## Sheet1
Task Name | Tid i utstrekning | Startdato | Sluttdato | % Fullført | Tid i arbeidstid | Utfører
Flexera Implementation Plan | 93,97 days? | Fri 25.01.19 | Thu 13.06.19 | 21% | 642 hrs
Planning | 2,5 days | Fri 25.01.19 | Tue 29.01.19 | 100% | 40 hrs
Onsite Kickoff | 2 hrs | Fri 25.01.19 | Fri 25.01.19 | 100% | 4 hrs | UO;SoftwareONE
Create Project Plan | 1 day | Fri 25.01.19 | Mon 28.01.19 | 100% | 8 hrs | SoftwareONE
Define preliminary resources | 4 hrs | Fri 25.01.19 | Fri 25.01.19 | 100% | 4 hrs | UO
Define FNMS architecture | 0,5 days | Fri 25.01.19 | Fri 25.01.19 | 100% | 8 hrs | UO;SoftwareONE
Provide remote access | 2 days | Fri 25.01.19 | Tue 29.01.19 | 100% | 16 hrs | UO
Planning complete | 0 days | Tue 29.01.19 | Tue 29.01.19 | 100% | 0 hrs | PM Project Manager
Setup Core Installation | 30,63 days | Mon 28.01.19 | Tue 12.03.19 | 58% | 98 hrs
Setup servers | 4 days | Tue 29.01.19 | Mon 04.02.19 | 100% | 16 hrs | Gunnar
Check prerequisites | 2 hrs | Mon 28.01.19 | Mon 28.01.19 | 100% | 2 hrs | SoftwareONE
Install FNMS | 3 days | Thu 14.02.19 | Mon 18.02.19 | 100% | 24 hrs | SoftwareONE
Deploy Beacon(s) | 2 days | Tue 19.02.19 | Wed 20.02.19 | 50% | 16 hrs | SoftwareONE
Install AppPortal | 2 days | Fri 01.03.19 | Tue 05.03.19 | 0% | 16 hrs | SoftwareONE
Documentation | 3 days | Tue 05.03.19 | Tue 12.03.19 | 0% | 24 hrs | SoftwareONE
Setup complete | 0 days | Tue 12.03.19 | Tue 12.03.19 | 0% | 0 hrs | Øyvin
Data gathering | 36,21 days | Thu 21.02.19 | Fri 12.04.19 | 36% | 100 hrs
Business Importer | 28,71 days | Mon 04.03.19 | Fri 12.04.19 | 55% | 44 hrs
Identify source for Corporate Units | 6,67 hrs | Mon 04.03.19 | Fri 29.03.19 | 75% | 4 hrs | Øyvin
Identify source for user information | 6,67 hrs | Tue 05.03.19 | Fri 12.04.19 | 100% | 4 hrs | Øyvin
Identify source for asset information | 6,67 hrs | Tue 05.03.19 | Fri 29.03.19 | 75% | 4 hrs | Øyvin
Create interface for corporate units | 1 day | Fri 15.03.19 | Fri 29.03.19 | 50% | 8 hrs | SoftwareONE
Create interface for user data import | 1 day | Fri 08.03.19 | Thu 21.03.19 | 100% | 8 hrs | SoftwareONE
Create interface for asset data import | 2 days | Fri 29.03.19 | Tue 02.04.19 | 0% | 16 hrs | SoftwareONE
Business importer complete | 0 days | Tue 02.04.19 | Tue 02.04.19 | 0% | 0 hrs | Øyvin
Inventory | 12,05 days | Thu 21.02.19 | Mon 11.03.19 | 20% | 56 hrs
Connect to AD | 4 hrs | Thu 21.02.19 | Thu 21.02.19 | 100% | 4 hrs | SoftwareONE
Prepare Flexera Agent | 1 day | Thu 07.03.19 | Fri 08.03.19 | 100% | 8 hrs | SoftwareONE
Deploy Flexera Agent | 1 day | Fri 08.03.19 | Mon 11.03.19 | 0% | 4 hrs | Gunnar
Connect to vCenter | 1 day | Thu 21.02.19 | Fri 22.02.19 | 0% | 8 hrs | SoftwareONE
Connect to VMware Horizon | 3 days | Fri 22.02.19 | Wed 27.02.19 | 0% | 24 hrs | SoftwareONE
Documentation | 1 day | Wed 27.02.19 | Thu 28.02.19 | 0% | 8 hrs | SoftwareONE
Data gathering complete | 0 days | Thu 28.02.19 | Thu 28.02.19 | 0% | 0 hrs | Øyvin
Procurement | 27,83 days? | Thu 28.02.19 | Tue 09.04.19 | 0% | 80 hrs
Provide templates | 1 day | Thu 28.02.19 | Fri 01.03.19 | 0% | 8 hrs | SoftwareONE
Collect contract information | 16,67 days? | Tue 05.03.19 | Thu 28.03.19 | 0% | 40 hrs
Collect entitlement information | 5,49 days? | Fri 29.03.19 | Mon 08.04.19 | 0% | 24 hrs
Import data | 1 day | Mon 08.04.19 | Tue 09.04.19 | 0% | 8 hrs | SoftwareONE
Procurement complete | 0 days | Tue 09.04.19 | Tue 09.04.19 | 0% | 0 hrs | Øyvin
Post Implementation Review | 14,92 days | Tue 09.04.19 | Wed 08.05.19 | 0% | 28 hrs
Document lessons learned | 3,33 days | Tue 09.04.19 | Tue 23.04.19 | 0% | 16 hrs | Øyvin
Distribute to team members | 1,67 days | Mon 06.05.19 | Tue 07.05.19 | 0% | 8 hrs | Øyvin
Create software maintenance team | 0,83 days | Tue 07.05.19 | Wed 08.05.19 | 0% | 4 hrs | Øyvin
Post implementation review complete | 0 days | Wed 08.05.19 | Wed 08.05.19 | 0% | 0 hrs | Øyvin
Flexera Implementation complete | 0 days | Wed 08.05.19 | Wed 08.05.19 | 0% | 0 hrs | Øyvin
Prosjektorganisering | 64,8 days? | Fri 25.01.19 | Fri 03.05.19 | 34% | 64 hrs
Prosjektplan detaljert ut | 5 days? | Thu 21.02.19 | Wed 27.02.19 | 75% | 24 hrs | Øyvin
ROS | 3,33 days? | Fri 26.04.19 | Thu 02.05.19 | 0% | 16 hrs | Øyvin
Gevinstplan | 3,33 days? | Fri 25.01.19 | Mon 04.03.19 | 25% | 16 hrs | Øyvin
Prosjektplan godkjent | 0 days | Mon 04.03.19 | Mon 04.03.19 | 0% | 0 hrs
Planlegging AppPortal og overordnet planlegging | 1,67 days? | Thu 02.05.19 | Fri 03.05.19 | 0% | 8 hrs | Øyvin
Teknisk eventuell fase 2 | 68,5 days? | Fri 25.01.19 | Thu 09.05.19 | 0%
Deploy Mac-agent | 1 day | Thu 28.02.19 | Fri 01.03.19 | 0%
Lokal programvare | 1 day | Fri 26.04.19 | Mon 29.04.19 | 0% |  | Lokale enheter
VDI | 1 day? | Fri 25.01.19 | Fri 25.01.19 | 0% |  | Gunnar, USIT
TSD | 1 day | Wed 08.05.19 | Thu 09.05.19 | 0%
Integrasjoner med innkjøpssystemet | 1 day | Thu 28.02.19 | Fri 01.03.19 | 0% |  | SI
Organisering av lisensforvaltning | 69,47 days | Thu 28.02.19 | Thu 13.06.19 | 3% | 192 hrs
Utpeke lisensansvarlig på fakulteter og enheter | 5 days | Mon 18.03.19 | Fri 22.03.19 | 25% | 24 hrs | Øyvin
Opplæring av personell | 5 days | Thu 28.03.19 | Fri 26.04.19 | 0% | 24 hrs | Øyvin
Avklare primær brukeraffiliation | 1,67 days | Mon 25.03.19 | Tue 26.03.19 | 0% | 8 hrs | Øyvin
Rollebeskrivelser i FNMS | 3,33 days | Fri 03.05.19 | Mon 13.05.19 | 0% | 16 hrs | Øyvin
Rutinebeskrivelser | 16,67 days | Mon 13.05.19 | Wed 05.06.19 | 0% | 80 hrs | Øyvin
Avklare eierskap til fellesmaskiner, PC-stuer, møterom o.l. | 1,67 days | Tue 26.03.19 | Thu 28.03.19 | 0% | 8 hrs | Øyvin
Ny modell for kostnadsfordeling | 6,67 days | Wed 05.06.19 | Thu 13.06.19 | 0% | 32 hrs | Øyvin
Behov for lokale løsninger bortfalt | 0 days | Thu 13.06.19 | Thu 13.06.19 | 0% | 0 hrs | Øyvin
Filgruppebasert forvaltning avsluttet | 0 days | Thu 13.06.19 | Thu 13.06.19 | 0% | 0 hrs | Øyvin